FUNDING AGREEMENT FOR DELIVERY of

professional development programmes

Contract Number 09-0220

Information & Communication Technologies (ICT) Professional Development Clusters 2009 – 2012

Between the Ministry of Education

And

the Board of Trustees of Sacred Heart Girls’ College, Hamilton

DATE:  February 9 2009

Ministry of Education

PO Box 1666

117-125 Lambton Quay

Wellington 6011

Ph 04 463 8025

Fax 04 463 002

FUNDING AGREEMENT

PARTIES:	The Secretary for Education acting by and through Howard Baldwin, Acting Manager, e-Learning unit, Schooling Group, Ministry of Education (“the Ministry”)

and	The Sacred Heart Girls’ College Board of Trustees a statutory body corporate established under the Education Act 1989 ("the Board")

# BACKGROUND

A	The Ministry has established the Information and Communication Technologies (ICT) Professional Development Programme with clusters of schools throughout New Zealand with the objective of providing a school based professional development programme for staff in the use of ICT. The Ministry provides funding to one school from each cluster, to enable the school, called a ‘Lead School’, to plan and manage the professional development activities on behalf of the schools in the cluster.

B	The Ministry has agreed to provide funding for a professional development programme in ICT for the cluster of schools specified in Schedule One of this Funding Agreement (“the cluster schools”) and the Board has agreed that it will provide the programme in respect of the cluster schools.

C	The Board and the Ministry have agreed to enter into this Funding Agreement to record their respective obligations in relation to the provision of professional development programme for the cluster schools.

THE BOARD AND THE MINISTRY AGREE AS FOLLOWS:

- Term

This Agreement will start on the date of signing and finish on February 1st 2012

However, either party can bring the Agreement to an end before the finish date under section 9 of this Agreement.

2	Obligations of the Board

  - The Board will provide the professional development programme in ICT (‘the Programme’) for the cluster schools as specified in the First Schedule.

  - The Board will provide written reports to the Ministry in accordance with the requirements of the Second Schedule.

  - The Board will forward information relating to the Programme to the Ministry upon request.

2.4 	The Board will comply with the relevant Health and Safety Guidelines and requirements of each school when working on their premises. The Board will act in accordance with the Public Service Code of Conduct at all times when providing services under this Agreement. The Code of Conduct is available at http://www.ssc.govt.nz/display/document.asp?NavID=151.

2.5	You promise that you have no conflict of interest or contractual obligation to another person or organisation that limits your right or ability to perform the work under this Agreement. The Board agrees to notify the Ministry of Education if any such conflict does arise.

3	The Board is not an employee

You are an independent Contractor, not an employee, partner, joint venture partner or agent of the Ministry. You will be responsible for the payment of all amounts due and payable to the Inland Revenue Department.

4	Funding

4.1	The Ministry will provide funding to the Board as specified in Schedule Three.

4.2	The Board acknowledges that the funding provided under this Funding Agreement is in addition to the annual operations grant payment payable under section 79 of the Education Act 1989 and any other discretionary allowance made to the Board by the Ministry.

4.3	The funding provided by the Ministry under this Funding Agreement must be expended by the Board only to undertake the tasks specified in Schedule One. Any funds unspent at the end of this agreement must be returned to the Ministry of Education.

4.4	The Ministry may suspend or cancel payment of any installment of the funding if:

- The Ministry considers that the Board has not complied with any of the terms and conditions specified in this Funding Agreement.

- There are changes in government policy or in the amounts appropriated by Parliament which may affect the payment of the funding.

4.5	The Board may be required to repay part or all of any funding it receives under this clause if:

- The Board fails to comply with any of the terms and conditions specified in this Funding Agreement.

  - The Contractor is not to transfer this Agreement

You agree that you will not transfer this Agreement to any other person or organisation.

  - Copyright

Explanatory note: The Ministry wishes to be able to share materials developed under this agreement with other schools and where possible to be able to utilise new ideas and systems without any new consents or payments being required. The Ministry recognises that some work may involve the use of material or software owned by others or may be an “add on” to such materials/programmes. Therefore it is critical that relevant warnings accompany the materials so that the Ministry and other school boards are aware of restrictions that may apply to the use of material developed under this agreement.

  - All intellectual property rights (including copyright) in all works and material produced under this agreement (“new works”) shall remain the property of the Ministry.

6.2	Both parties shall continue to own all intellectual property rights that they held prior to the commencement of this Agreement.

  - The Ministry agrees that the Boards of all schools involved in the programme may continue to use material developed under this agreement.

6.4	The School Board will gain all consents (including consents from third parties) as may be necessary to enable the Ministry and any other party approved by the Ministry, to unconditionally use the works developed under this Agreement at no additional charge. For more details regarding copyright and privacy issues refer to http://www.tki.org.nz/r/governance/copyright/index_e.php

7	Subcontract

The Board will not subcontract services without prior written consent from the Ministry of Education. Any subcontract must state that the copyright in all work produced by the subcontractor remains the property of the Ministry.

  - Variation and review

  - This Agreement may be varied by agreement in writing and any such variation will then form part of this Agreement.

  - During the term of this Agreement the Ministry or its agent shall carry out two annual reviews.

  - Each annual review is to begin by 1 September and conclude by 1 December.

  - The matters to be discussed in the annual review are:

- the performance of the Contractor in delivering and reporting on the services are as specified in the First and Second Schedules;

- the financial statements prepared by the Contractor;

- re-negotiation of the First, Second and Third Schedules of the Agreement to incorporate any changes as agreed by both parties.

  - Termination

  - Either party may terminate this Agreement if the other party has either breached an obligation or failed to perform an obligation required under this Agreement.

  - Before it terminates the Agreement the party concerned shall give the party in breach written notice of the breach or non-performance and request that party to remedy the matter within 28 calendar days.

  - If the party in breach fails to remedy the matter within 28 calendar days of written notice issued under paragraph 9.2, then this Agreement shall be terminated in writing, effective immediately.

  - Where a notice of termination is served:

- We are only obliged to pay for work already performed; and

- You are not obliged to undertake further work.

9.5 	Neither party shall be liable to the other for damages, compensation or any other remedy at law or equity for termination of this Agreement.

SIGNATURES OF THE PARTIES TO THIS AGREEMENT

Ministry of Education

Signed by

Howard Baldwin, Acting Manager, eLearning unit, Schooling Group

………………………………………...

(Signature)

For and on behalf of THE SECRETARY FOR EDUCATION

Dated at_______________________ this________ day of________2008

Lead School

Signed by

Allison Gibbons (Principal)

Full name and Title (Must have authority to sign on behalf of the Lead School)

…………………………………………..

(Signature)

e-LfA

Cluster Name

Dated at Hamilton this 9th day of February_2009

FIRST SCHEDULE

Services to be provided by the Board

Goals of the Programme

The objectives of the Programme to be provided by the Board under this Funding Agreement are to provide professional development programmes that:

- Implement the New Zealand Curriculum / Te Marautanga o Aotearoa through the use of e-learning;

- Increase capability of teachers and principals to improve students' learning and achievement through e-learning;

- Strengthen professional learning communities and increased collaboration within and across schools;

- Increase e-learning leadership and ICT strategic planning capability of principals and teachers;

- Increase the school community’s understanding of the educational contribution of e-learning.

Programme to be provided

The Board will provide the Programme according to the Programme Outline (A–E) and Milestones set out below.

Programme Outline

A. Scope of the cluster

| Cluster school names | School MoE number | Number of teachers (FTTE) | Number of students |
| --- | --- | --- | --- |
| Sacred Heart Girls’ College, Hamilton | 0139 | 62 | 813 |
| Hamilton's Fraser High School | 0135 | 112 | 1734 |
| Total |  | 174 | 2547 |

FIRST SCHEDULE… continued

B. Assigned personnel

Project Director/s – the person who will be the official contact with the ministry

Name/s: Margaret Paiti -FFTE = .2

Key tasks from the job description for this role:

- manage the contract for the cluster.

- communicate to the cluster and senior leadership team  both in an informal and formal basis

- work in close liaison with the Ministry of Education

- coordinate the preparation, presentation, evaluation and continual development cycle of professional learning programmes which deliver  the objectives of the contract.

- design and implement an  administrative framework for effective implementation, cycle of improvement and sustainability

- liaise directly with the school Business Managers on project budget and reporting expenditure

- meet the identified milestones and ensure submission of a final report.

- investigate support from external providers/services or experts.

- maintain a constant overview of the status of the ICT PD Programme.

- wherever possible make links with other school initiatives and the New Curriculum within ICT Professional Learning opportunities.

- make links to outside agencies or personnel as necessary.

- facilitate the networking coordination  of staff across the schools

Co -Project Facilitators

Name: Sue Ware - FFTE =.2

Name: Deborah Hunt - FFTE = .2

Key tasks from the job description for this role:

Administration/Communication

- co-ordinate and  provide training for all teachers

- organise and co-facilitate ICT Lead teacher workshops

- report and attend meetings with the Project Director /School Principals  (2x a term)

- assist and contribute to milestone reports as and when required

- liaise with Principals and BOT's of project schools - one presentation per school to be negotiated

- prepare introductory material for programme at the commencement of the contract

- assist integration of ICT contract that embraces the Revised NZ Curriculum, and any other initiatives within the school.

- assist with Cluster Management Team, Facilitators and MOE to fulfil contractual obligations, including ensuring milestone reports are prepared and submitted to the Ministry of Education by the due dates.

- co-facilitate the networking of staff across the cluster.

- communicate financial requests necessary for effective project delivery to the Cluster Management Team.

- contribute to the establishment of a three year strategic plan and a one year action plan

- keep accurate, current and disseminated digital records of your schools ICT PL programme progress

Professional Learning

- assist planning and communicate to all stakeholders the professional development plan for the ICT PD cluster schools in line with the Cluster proposal and strategic plan

- attend and actively participate with the team at national ICT conferences organised by the Ministry of Education

- provide professional learning for facilitators utilising the action research model of inquiry

- make links to outside agencies or personnel as necessary.

- coach Facilitators to guide and assist with the implementation of an in-school ICT Professional Learning Programme linked with teacher observations

- co-ordinate and Facilitate 1:1, small group and staff ICT professional learning opportunities in inquiry learning and critical thinking.

- conduct classroom teacher observations

- provide teachers with in-class support as required.  (Utilise the observational tool to help establish baseline change).

- encourage and support teachers to share their ICT PL journeys by way of regular show and tell presentations to staff, and collation of student and teacher voice.

- co-create and promote the pedagogical growth of teachers by regularly providing professional readings/resources/forums as appropriate to the ICT PL programme.

- co-ordinate, collate, analyse and create recommendations from Staff ICT Professional Learning needs survey

- assist in the preparation and co-ordination of an introductory/launch day for your school at the commencement of the contract.

- participate in personal professional development that assists in the schools core goals – inquiry, critical thinking and assessment

- keep personally informed and updated of all national initiatives /research that relate to success of the ICT PD project, and share information.

Other personnel

Facilitator/s (2) and Maori/Pasifika Facilitator (2) = .1 FFTE each

Name: Rene Molina, Sacred Heart Girls' College

Name: Jesse Te Weheei , Hamilton's Fraser High School

## Key tasks from the job description for this role:

- undertake training with the leadership team

- promote and manage the project in your own school and be the first point of contact for your school

- assist staff to complete surveys

- lead a PLC group – data, assessment, curriculum, Maori or PI

- conduct classroom teacher observations and provide coaching using the observational tool

- provide teachers with in-class support as required (utilise the observational tool to help establish baseline change)

- assist  Cluster Management Team, Project Facilitators to fulfil contractual obligations, including ensuring milestone reports  are supported with key documentation

- contribute to the establishment of a three year strategic plan and a one year action plan

- participate in personal professional development that assists in the schools core goals – inquiry, critical thinking and assessment

- attend and actively participate in various forums and meetings eg learning@school conference organised by the Ministry of Education

- initiate opportunities to provide teachers with Professional reading and hold regular staff PL meetings/workshops. (These workshops can be online)

- lead the keeping of accurate, current and disseminated digital records of ICT PL programme progress. (Include ongoing records)

- make links to outside agencies or personnel as necessary.

- collaboratively support other facilitators when necessary in e.g. hui, one to one mentoring, data, curriculum knowledge, skills

- keep personally informed and updated of national initiatives or research that relate to success of the ICT PD project, and share information.

Maori and PI facilitators

Name:  Talei Morrison, Sacred Heart Girls' College

Name:   Jessie Te Weehi, Hamilton's Fraser High School

Key tasks from the job description for this role:

- assist  Cluster Management Team, Project Facilitators to fulfil contractual obligations, including ensuring milestone reports  are supported with key documentation

- contribute to the establishment of a three year strategic plan and a one year action plan

- participate in personal professional development that assists in the schools core goals – inquiry, critical thinking and assessment

- attend and actively participate in various forums and meetings eg learning@school conference organised by the Ministry of Education

- undertake training with the leadership team

- lead the keeping of accurate, current and disseminated digital records of ICT PL programme progress. (Include ongoing records)

- make links to outside agencies or personnel as necessary.

- collaboratively support other facilitators when necessary in e.g. hui, one to one mentoring, data, curriculum knowledge, skills

- keep personally informed and updated of national initiatives or research that relate to success of the ICT PD project, and share information

- promote and manage the project in your own school and be the first point of contact for your school

- construct a separate online forum for our Maori and Pasifika students (provision  of support through Moodle leaders)

- modify current Maori and PI data base system to be inclusive of ICT

- deliver and complete  survey report of Maori and PI students

- investigate the viability and implementation of a targeted on-site student centre for Maori and Pasifika to enable students to have user-friendly access to their information to become autonomous learners who confidently engage in their academic pathways.

- liaise with whanau and strengthen relationships with whanau through face to face hui, to foster positive understandings of ICT possibilities in enhancing  their child’s choices and learning processes/opportunities

- co-ordinate opportunities for Maori and PI students to share their ICT PL success stories within their own school and across the Cluster

Leadership Team

Name/s: Ally Gibbons and Martin Elliott - Principals

Virginia Crawford and Margaret Paiti – Deputy Principals

Key tasks from the job description

- provide strategic oversight and leadership direction of the project – dedicated section in both schools annual plans

- assist with the preparation of the milestone reports

- assist the Project Facilitator and Facilitators to undertake their roles

- undertake appropriate check point monitoring and evaluation of the programme to ensure the targets are met

- facilitate the action plan process including analysis, scoping and milestone reporting, resource allocation, and budget decision-making

- be able to identify strategic communication linkages with other relevant initiatives and services

- demonstrate ability to address the cultural values, aspirations and particular needs of Maori and Pasifika or special need groups.

- negotiate with school/s educational strategies that will be implemented

- provide the necessary project management leadership and coaching communicate to schools the plan of intent and delivery of  the project  (Staff, students, BOT and wider school community)

FIRST SCHEDULE… continued

C. Programme Goals and Success Indicators

| Programme goals |  | Success Indicators for National and Cluster Goals |
| --- | --- | --- |
| National goals | Cluster goals |  |
| - Implement the New Zealand Curriculum / Te Marautanga o Aotearoa through the use of e-learning; | Student Goals - Create students who are confident, capable and connected users and learners of ICT - 2009 - Selected Year 9 students will achieve at or above their appropriate literacy and thinking skills – Level 4/5. The selection of students will be based on their asTTle results. - Raise achievement and engagement of all selected students to ensure they attain NCEA Level 1 Literacy. - Improved retention and engagement of selected students. | - All students (inclusive Maori and Pasifika ) are confident, competent and engaged participators of ICT technologies - Students critique and use technologies to enhance their critical thinking capabilities. Hence, Information and Communication Technology applications help to strengthen, support and extend thinking AsTTle tool used to measure in-school progress from Year 8 to 11. Baseline data to be “thinking skills” and successfully investigate and employ ICT strategies that target or blend Blooms Taxonomy approaches or higher order thinking. - Other data supporting positive achievement gain and /or engagement change: retention data, student attitudinal surveys, classroom observation information and academic engagement. - Students to effectively feedback through online surveys and classroom observations to support continuous evaluative process The following Quantitative assessment platforms investigated: - Electronic Independent Learning Plan (EILP) enable learners to document and track their progress, assign priorities, collate evidence and identify the resources they need to succeed. Digital planning and prioritisation tools can enable this process. Learners should be assessed at times appropriate to their own development and in different ways depending on the activity in question. Most importantly, assessment should be a positive and constructive experience, engaging the learner and the system in a process of constant monitoring, updating and dialogue. - Peer-to-peer and self-assessment processes introduced to create powerful learning communities. Students start owning their learning (both content and process) - E-portfolios investigated for individual learners. E-portfolios allow an accessible record of the different stages of the learning to be kept and personalise the learning opportunities for students |
| - Increase capability of teachers and principals to improve students' learning and achievement through e-learning; - Strengthen professional learning communities and increased collaboration within and across schools; | Teacher Goals - Increase the technical competency of all staff with a range of computer hardware and software and have an understanding of how this technology can be appropriately used to improve teaching and learning e.g. assessment tools, LMS and SMS. - Use current educational research and understand the link between theory and practice. - Build teachers confidence and capability to extract, analyse and identify patterns in achievement data that will aid in the evidence-based decision making cycle to improve teaching and learning (thinking skills). - Critically reflect and evaluate their own personal teaching practice in relation to the integration of ICT in their curriculum programmes and implement a process to act on the new learning’s – (inquiry model and social constructivist) - Identify the essential characteristics of a successful learning culture and apply these principles to the use of information and communication technology in a learning programme e.g. PLC - Effectively and efficiently, facilitate and evaluate a range of high quality on-line courses for students that provide opportunities for collaboration, self-assessment and prompt feedback. - Capacity building of ICT leadership and expertise within each schools structure. | - Evidence driven framework – informed by teacher ICT/leadership audit to identify baseline ICT skill data of teachers and current practices. - Holistic ICT picture of school created - Cross-curricular mapping matrix identifies the strengths and gaps of ICT integration in all learning areas to effectively drive schools needs. - Collaborative network system established between and within schools, supporting the collective vision and focus on teaching and student learning. - Evaluative capacity review process integrated into the programme to provide ongoing monitoring of successes or areas of improvement - Provision of tailored quality professional learning opportunities, personalised to ALL teacher needs. The focus is underpinned by evidenced-informed pedagogy providing teachers access to new understandings to help challenge and strengthen daily teaching practice. - Interaction of online programmes - participation rate is above 60%. (Currently there are no programmes operating in either school.) - Regular Professional Learning Community meetings – positive attendance rates by ALL staff members. E.g. Leadership group meets once a term. Teachers participate in the schools regular cycle of PLC 1 x a fortnight. Leadership modelling and the valued recognition of PLC provides the conditions for professional growth and promotes the inquiry cycle of learning for teachers. - A range of PLC topics provided for staff to develop understandings and strengthen applications: inquiry model, effective use of data, assessing critical thinking, application of ICT tools to enhance higher order thinking, ICT applications e.g. moodle, spreadsheets, word etc. Teachers are proficient in creating optimal learning opportunities through higher order ICT applications. Examples; increased feedback through online engagements, generate more challenging learning contexts or online peer discussions - All Year 9 teachers and/ or project teachers to be involved in classroom observation process. This deprivitisation aims to identify the successful integration of Information and Communication Technology application in the classroom learning and engagement of students , gives ongoing monitoring, and provides potential student engagement data. (To be considered whether specific Maori and Pasifika class engagement will be applied). In 2009 the aim will be setting up, training and trialling observation tool or procedure to ensure that this can be successfully operational by 2010, Term 2. The observations occur 3 x a year for all teachers involved. - Positive change in teacher attitudinal surveys towards the implementation, confidence and utilisation of ICT in learning programmes. - At least twice a year teacher or programme successes published or showcased in workshops or presentations. - An effective leadership coaching and mentoring model operates in schools with the foci of sustainability, succession planning, professional and personal growth. E.g. Teachers get promotions, take on extramural learning opportunities. - Expert teachers given opportunity throughout the project to share knowledge and skills to teachers, either through presentations in workshops, coaching sessions or PL meetings. - Integrated approach to Information and Communication Technology. All faculties are involved with the process and programme, to deliver a more comprehensive and cohesive framework in curriculum alignment and improve the application of ICT in teaching and student learning. Investigate the implementation of integrating Information and Communication Technology into all curriculum programme frameworks by 2011. |
| - Increase e-learning leadership and ICT strategic planning capability of principals and teachers; | Community Goals - Increase community participation in school ICT strategies and the application of ICT resources - Increase community/parent understanding of the importance of ICT in student learning especially for Maori and Pasifika - Create effective online partnership with family and community - Enhance collaborative schooling relationships and e-Learning partnerships | - Opportunities provided for quality information hui/workshops to promote access and increased knowledge of the educational benefits of ICT for learning, especially with Maori and Pasifika whanau. (Two hui a year) - Positive number of online interactions and engagements by the community are evident. - Newsletter communications celebrate and inform community about ICT successes and the positive impacts on learning e.g. Team-up, TKI and our Online–Learning Communities. - Increased collaboration within and across the cluster schools enabling effective e-Learning to take place. (at least 2 interactions a term ). This is recognised by shared school PL, team meetings, collaborative presentations/workshops |
| - Increase the school communities understanding of the educational contribution of e-learning. |  |  |

FIRST SCHEDULE… continued

D. Implementation of the Programme

| Programme Professional Development activities |  |  | Success Indicators for Programme implementation |
| --- | --- | --- | --- |
| What do we propose to do? | How much do we propose to do? | What resources do we need to carry out the programme? | How well have you carried out the programme activities? |
| Collective inquiry model to be implemented into the professional learning culture of this project. Example of a question for inquiry How ICT could constructively support the learning of higher order thinking skills and how we could effectively develop ‘new’ ways of measuring and assessing data? Leadership learning conversations and logic intervention model to: up-skill team, provide strategic direction, pace and give leadership reflection process. | Whole leadership group to meet to develop the PL culture protocols, inquiry process and required systems (linked to term one PLC and continued knowledge building cycle) Whole team meetings once a term Provision of other interaction avenues utilized eg email | Discussion Readings Expert advice and support Staffing Meeting times or communication interaction Time allowance /management units these will be linked with roles | Inquiry model established , ICT systems, programme and infrastructure set for effective and thoughtful model of ongoing and long term operations An effective leadership group established to develop a coherent strategic plan developed for the 3 years to ensure targeted support and systems for improved and sustainable outcomes Regular team meetings attended |
| Explore possible external contacts/ experts to support the project direction (possibilities SSS, Polytech and universities) | Consult with a wide range of people or organizations - use team networks | Travel for face to face hui /phone call /Skype/video conferences | Set contracts or professional support / guidance for our schools to provide an external lens to cultivate or encourage creativity and transformation opportunities in the project |
| Deliver whole school PL opportunities Year 1: Combined e-Learning Launch Day Year 2: Combined e-Learning Phase 2 Day Year 3: Combined e-Learning Phase 3 Day | 124 (64 SHGC and 60 HFHS) Greater number of staff for the next two years. Yet to be determined. | Time full day (TOD) Human Resources - internal and external speakers/experts will be required Facilities – SHGC Technology required for presentations e.g. robotics, internet, intranet | Full attendance by teachers to ensure clarification and understanding of the projects direction Positive and constructive feedback is given by teachers to help determine construction or embedding of considered good practices for students learning |
| Term One staff PLC | Whole school staff will participate. Aim of term one PLC is to give outline and educational framework to the programme prior to the Launch day. SHGC PLC will be delivered every Tuesday fortnight for term one (starting week 2) and HFHS will be Wednesday. Current selected topics – Individual schools professional learning aims and framework Our schools culture / kawa of a PLC Inquiry model of learning/ social constructivism theory Data and evidence based decision-making Staff meeting presentation by Mark Treadwell on 21st century learners (11 February) | Photocopying Set up meetings prior to staff PLC delivery Resources – vivid, postiks Guest speaker costs - | Consistent understanding of school overview and direction with all professional learning Key foundational learning messages shared with all staff to encourage and embed our schools professional learning framework and generate staff buyin. |
| PLC These sessions will range form full staff meetings to project team that will consist of 120 staff to one on one | Whole staff will be involved in compulsory sessions relating to e-Learning. Eg Term 1 programme Professional learning communities established and focused on specific areas of need Follow-up workshops or one on one (coaching) sessions will be made available throughout the project teachers to support teachers pace and progression Presentation/workshop examples School management system – KAMAR/ School links Microsoft office applications Cell phones, robotics Websites Podcast, video cast, blogging Digital stories Moodle/Web 20 technologies | Time – PL meeting times Access to resources eg cameras/video Staffing Professional readings /videos Sites Guest speaker costs eg transport, thank you gifts | Teachers confident, effective users and integrators of ICT skills into the wider learning environments Teachers exchanging, sharing reviewing ideas collaboratively with other teachers. Information and Communication Technology tools and applications can help teachers engage students and reduce teacher dependency in instructional learning Survey and feedback opportunities will be processed throughout the Information and Communication Technology journey of eLfA |
| Data Analysis Team to credibly measure, monitor and inform learning outcomes. NB (All PLC teams will be required to follow key principles and established culture e.g. Learning orientated, solution focused. Question – who and how do we organize a comparative control group | Skillfully investigate the varied technical ways to track, monitor and analyze dependable achievement and engagement data Professional learning discussion delivered on using data to support learning / thinking skills. | Kamar Expertise – ½ day Inservice Term One – Initial Meeting and Goal Setting ½ day Term Two – Collaboration of work carried out ½ day Term Three – Report Back ½ day Term Four – Future Planning Time for research /readings e.g. Consider the Evidence Shifting the focus: achievement information for professional learning Teaching staff to be involved as part of their professional learning | Team created and supported within school framework to optimally explore areas of inquiry Effectively develop ‘new’ ways of measuring and assessing data that will support teachers without any major increase in work loads Improved data and tracking system to guide measures of improvement in student outcomes All teaching staff will be using data to effectively inform classroom practice and student learning by end of 2011. Data should support the positive influence of teacher interactions, student motivation and deep learning. Strengthen our commitment to results orientated culture. Use of achievement data, evaluation review feedback or surveys (common language used and understood) |
| Assessment Team to mobilize the collaborative investigation and direction for valid reliable ICT assessment tools linked to deep thinking (These two teams maybe a combined working party) | Inquire about the use of ICT to produce quantitative data to provide evidence of transferable standardized higher order thinking across all learning areas. Questions - Do our current measurement tools reflect the learning that has taken place; do they reflect the higher order thinking skills that we should be teaching our students in the 21st Century? - We know that in the knowledge economy of the 21st Century, higher order thinking skills are valued and are indeed essential. But, do our assessments reflect higher or lower order thinking, how can we ensure this occurs? Questions - How well are our students comparing to others? How do we effectively respond? - What cross – level or cross curricular data can be collected? - Are tests fair ways to assess learning verses mastery/ performance? Formulate other credible data opportunities to help show shifts - retention data, student attitudinal surveys, classroom observation information and academic engagement. (Qualitative) | Term One – Initial Meeting and Goal Setting ½ day Term Two – Collaboration of work carried out ½ day Term Three – Report Back ½ day Term Four – Future Planning Travel – visit other schools Time for research /readings Teaching staff to be involved as part of their professional learning community (one lead teacher but supported by other team members) | Team created and supported (Build up collaborative involvement of all faculty areas) Expert readings and discussion have occurred and have been documented to develop exploration of school wide best practices AsTTle tool will measure in-school progress from Year 8 to 11. Baseline data to be “thinking skills” via ICT strategies that target or blend Blooms Taxonomy approaches. Will gauge a clear picture of progress for students and be able to set informed targets Transferability of standardised higher order thinking skills will create greater autonomous and critical learners Valid, reliable assessment approach built into the project to help gauge how ICT can directly improve student learning or engagement |
| Professional On-line Learning Community (via-Moodle) Staff/Teachers | Staff/faculties – set up an online learning community. Create a supportive Infrastructure via the online community | Visit other schools Face to face professional development Time for research Site development Year 1 1-1/2 day per week Year 2 – ½ day per week Year 3 – ¼ day per week Schoolgate – linked to Kamar | Moodle set and operating across all curriculum areas. Improved access via on line link to meetings for teachers. Majority of staff use the online learning community forum to allow deeper discussion and self reflection on traditional verses alternative assessment for 21st Century learners Online communities foster collegial support, up-skilling in technical applications and abilities (e.g. SMS), encourage the professional sharing of and access to knowledge and the creation and reciprocity of electronic resources. All teachers will have accessed the site and 1/3 will be proficient in everyday usage Communities use the online learning site. Analysis of site usage |
| Professional On-line Learning Community (via-Moodle) General Students Maori and Pasifika students | Lead facilitators for each group to be assigned Online e-Learning communities for students for SHGC 2009 and developed for HFHS for 2010 An analysis of site usage will provide evidence of value or uptake | Time allowance Site development Year 1 1-1/2 day per week Year 2 – ½ day per week Year 3 – ¼ day per week School-links Teachers attend professional support delivery | Students use the online learning site for immediacy of feedback or constructivist learning Students access their academic record online (especially valuable for Maori and Pasifika) Students get instant feedback from online learning activities that are designed by teachers for this specific purpose. Students collaborate and work with their peers to create new knowledge Students access learning resources anywhere and anytime. Students are able to construct their own knowledge by exploring and engaging in hands-on authentic interactive activities, which strengthen their understanding of concepts and processes. Use of the Moodle site is analysed. Students are effectively using the online learning site and see it potential value. (50% plus access) A common language of learning is reinforced outside school via computer access. This gives opportunity for students to talk about and understand the learning process. Parents can have access to this opportunity strengthen ties. |
| Integration of eLearning strategies /approaches in the classroom | - Teachers to be provided with whole group or personalized support to help motivate the teachers application and knowledge of successful eLearning approaches | ICT in Lesson Plans or Unit plans. | Increase in confident and capable teachers who readily apply ICT approaches in their daily classroom practice to enhance student learning (with focus on higher order thinking). Lesson plans will have ICT components within units |
| Deprivatisation – opportunity to engage in dialogue, experimentation/ observation and reflection. This classroom practice model will help maximize a cycle of continuous improvement for teacher and student learning. | - Deprivatisation of classrooms - Regular teacher observation and feedback on each teacher’s classroom practices #### Contribution in learning theories and practices #### Training teachers in designed or aligned observation tool #### Coaching / mentoring process built in “Critical friend” strategy employed to give evaluative commentary and support. #### SAM targets set by teachers | Consider different models of deprivatisation currently operating in secondary schools Teacher Relief Days for PL and observations Identify and utilize elements internal and external expertise e.g. SCT/TK/SSS/ESQ Observation tool resources Classroom data/feedback analyzed | A model is created and operating by end of term 4 2009. Training is provided for staff on use of observation tool to ensure staff ownership, understanding and sustainability Coaching / mentoring PL opportunities to enhance collective model of sharing and personal development. Teachers observed and all set S.A.M target with foci on technology integration. (This will instigate a more reflective and evaluative process into the teaching professional learning cycle or review). More confident and capable teachers readily apply ICT approaches in their classroom programme to enhance student learning. Observations illustrate staff are modeling learning and show the value of learning to students. |
| Lead Team Leadership Team Project Director Project Facilitator Facilitator(s) Create a distributed leadership model that will better deepen and extend each school’s expertise, capabilities and capacities. | - Attendance at Cluster Meetings - Attendance at relevant Professional Development Courses - Attendance at relevant ICT and Leadership Conferences - Change Management - Succession Planning | Finance for conference costs Teacher Relief Guest Speakers Subscriptions Literature | Sharing of Knowledge through the centralization of information on professional learning community site will provide professional growth, reflective and critical understanding of eLearning in education. Conferences, presentations with theory and practice of new knowledge, to encourage personal and professional growth of teachers. Capacity building of ICT leadership and expertise within each school structure – initially five ICT leaders - this team will increase as the project progresses. Model to help build schooling capacity and capabilities for effective long term integration. |
| Teaching Staff Motivate staff to specifically plan their learning around the quality integration of eLearning that will benefit students learning processes Teachers to become excited about learning. Able to feel supported to take risks and experiment with new approaches in technology and learn from their practice. Observations Professional learning communities | - Teacher ICT/leadership audit will identify baseline skill data - Mapping matrix will identify the integration of ICT in all learning areas - Interaction of online programmes - participation rate - Regular PLC meetings and attendance - Classroom observational data and running records of achievement (Maori and Pasifika data will be separated) - Teacher attitudinal surveys - Leadership coaching and mentoring developed - Identify the essential characteristics of a successful learning culture and apply these principles to the use of information and communication technology in a learning programme e.g. PLC - Use current educational research and understand the link between theory and practice. | Professional Learning Community Online and face to face time TRD time for observations and feedback sessions Resources/ readings Expert speakers Video conferencing equipment /skype Exploration of different technologies | Increase the technical competency of staff with a range of computer hardware and software and have an understanding of how this technology can be appropriately used to improve teaching and learning e.g. assessment tools, LMS and SMS. 100% of staff using SMS. LMS will be personalized for whole staff at differentiated levels. All teachers are confident to implement the use of e-Learning as the observational tool provides a process for reflective and constructive inquiry to scaffold integration of technology approaches. Build teachers confidence and capability to extract, analyse and identify patterns in achievement data that will aid in the evidence-based teaching and learning (thinking skills) Teachers evaluate a range of high quality on-line courses for students that provide opportunities for collaboration, self-assessment and prompt feedback. Teachers identify the essential characteristics of a successful e-Learning culture / Revised NZ Curriculum document and apply these principles to their curriculum programme |

FIRST SCHEDULE… continued

E. Milestones

1. 	Activities carried out and results achieved during the Milestone 1 period

1.1	Expected date of completion of Milestone 1 is 5 June 2009.

  - Details of the tasks to be completed by the Contractor to achieve this milestone are:

    - Liaise with the National Facilitator assigned by the ministry to this project

    - Report on your progress towards achieving 2-3 of your programme goals for Milestone 1

| Cluster goals for Milestone 1 | Success Indicators |
| --- | --- |
| - Baseline teachers / Year 9 students Survey Completed - All year 9 AsTTle data collected and collated - Infrastructure for Online Professional Learning Site Completed - Infrastructure for Student Online Learning - Strategic Plan and Annual Plan set with structural frameworks established (collaborative process) - Inquiry question and process established. Professional learning culture established and working parties constructed - Launch day and key stakeholders hui completed - Term one teacher PLC sessions delivered in both schools and collaboratively designed | All baseline data information collated and analysis report completed Online communities established and successfully operating Coherent strategic plan developed for the 3years to ensure targeted support and systems for improved outcomes Annual plan and targets set and communicated (based on research and current data) Experts’ readings and discussion have occurred and have been documented to develop exploration of school wide best practices for Inquiry process. Culture for an effective supportive reflective Professional learning community has been established and teachers are active participates All staff to attend presentations and contribute to the evaluation process ( Total of 4 presentations) |

    - Report on your programme implementation during the milestone period.

1.2.4 	Submit a progress report to the Ministry by the milestone date on each of the above tasks and relevant performance measures, as per the Second Schedule of this agreement.

- Activities carried out and results achieved during the Milestone 2 period

  - Expected date of completion of Milestone 2 is 27 November 2009.

  - Details of the tasks to be completed by the Contractor to achieve this milestone are:

    - Liaise with the National Facilitator assigned by the Ministry of Education to this project

    - Report on your progress towards achieving the National programme goals

    - Report on your programme implementation during the milestone period.

    - Submit a progress report to the Ministry by the milestone date on each of the above points, as per the Second Schedule of this agreement.

    - Complete the contract review and variation template

FIRST SCHEDULE… continued

3	Work to be completed to achieve Milestone 3

3.1	Expected date of completion of Milestone 3 is 4 June 2010.

3.2	Details of the tasks to be completed by the Contractor to achieve this milestone will be developed during the 2009 annual review.

4	Work to be completed to achieve Milestone 4

4.1	Expected date of completion of Milestone 4 is 24 November 2010.

4.2 	Details of the tasks to be completed by the Contractor to achieve this milestone will be developed during the 2009 annual review.

5	Work to be completed to achieve Milestone 5

5.1		Expected date of completion of Milestone 5 is 3 June 2011.

5.2	Details of the tasks to be completed by the Contractor to achieve this milestone will be developed during the 2010 annual review.

6	Work to be completed to achieve Milestone 6

6.1	Expected date of completion of Milestone 6 is 23 November 2011.

6.2 	Details of the tasks to be completed by the Contractor to achieve this milestone will be developed during the 2010 annual review.

SECOND SCHEDULE – Reporting

The Board will provide a Milestone Report and Disbursements Schedule within 5 working days of the expected date of completion of each Milestone specified in the First Schedule.

Each Milestone report shall be written in a template provided by the Ministry which may vary in response to the reporting requirements of the National Programme.

Each Milestone Report shall contain a summary of the Contractor’s self-assessed performance on each of the milestone activities. Each summary must include explanations of any variances from the milestone tasks.

The National Support Services Facilitator assigned to your cluster will provide a report on your cluster’s progress to the ministry as per the Reporting schedule in the Third schedule.

All cluster schools will complete the Educational Positioning System (EPS) surveying task upon entry to the ICT PD programme and any end of project survey that is required by the Ministry.

THIRD SCHEDULE — Payments

1. The Ministry will provide funding to the Board up to a maximum amount of $360,000 GST inclusive.

Project Budget

See attachment

One Year Budget Figures

Professional fees 	$ 57055

Professional costs 	$22000

Operational costs 	$7779

Teacher Development funds	 $ 19833

Total	$106667

GST	$13,333

Total Funding	$120000

3. Use this budget to fill in the three yearly budget figures in the table below

Three Yearly Budget Figures

Professional fees 	$ 17164

Professional costs 	$ 66000

Operational costs 	$ 23336

Teacher Development funds	 $ 59500

Total	$ 320,000

GST	$ 40,000

Total Funding	$360,000

THIRD SCHEDULE – Payments… continued

- Payment and reporting schedule

2009-2012 clusters contract for $360,000

New contract –

Changed to allow $50,000 (NET i.e. excluding GST) less spend in 2008/09 year and a $50,000 (NET i.e. excluding GST) greater spend in the 2009/10 year

| Payment: | Reporting schedule | Net | GST | Total |
| --- | --- | --- | --- | --- |
| 1-Jan-2009 | Conditional on receipt and approval of Programme Outline | 16,587.30 | 2,073.41 | 18,660.71 |
| 1-Apr-2009 | NSSF Progress report to Ministry – A | 16,587.30 | 2,073.41 | 18,660.71 |
|  | (due 20.3.09 ) |  |  |  |
| 1-Jul-2009 | Milestone 1 (due 5.6.09) | 16,587.30 | 2,073.41 | 18,660.71 |
| 1-Oct-2009 | NSSF Progress report to Ministry – B | 28,452.38 | 3,556.55 | 32,008.93 |
|  | (due 18.09.09) |  |  |  |
| 1-Jan-2010 | Milestone 2 (due 27.11.09) | 28,452.38 | 3,556.55 | 32,008.93 |
| 1-Apr-2010 | NSSF Progress report to Ministry - C | 26,666.67 | 3,333.33 | 30,000.00 |
|  | (due 19.3.10) |  |  |  |
| 1-Jul-2010 | Milestone 3 (due 4.6.10) | 26,666.67 | 3,333.33 | 30,000.00 |
| 1-Oct-2010 | NSSF Progress report to Ministry - D | 26,666.67 | 3,333.33 | 30,000.00 |
|  | (due 17.9.10) |  |  |  |
| 1-Jan-2011 | Milestone 4 (due 24.11.10) | 26,666.67 | 3,333.33 | 30,000.00 |
| 1-Apr-2011 | NSSF Progress report to Ministry - E | 26,666.67 | 3,333.33 | 30,000.00 |
|  | (due 18.3.11) |  |  |  |
| 1-Jul-2011 | Milestone 5 (due 3.6.11) | 26,666.67 | 3,333.33 | 30,000.00 |
| 1-Oct-2011 | NSSF Progress report to Ministry - F | 26,666.67 | 3,333.33 | 30,000.00 |
|  | (due 16.9.11) |  |  |  |
| 1-Feb-2012 | On receipt and approval of final milestone (6) (due 23.11.11) | 26,666.67 | 3,333.33 | 30,000.00 |
| Total |  | 320,000 | 40,000 | 360,000 |

4.1 The Ministry will pay the Funding to the Board in accordance with the above table on the completion, to the satisfaction of the Ministry, of the services described in the FIRST SCHEDULE, the provision of reports as specified in the SECOND SCHEDULE.

4.2 All payments (apart from the January 2009 and Milestone 6) will be by automatic payment into the lead school account. The January 2009 and Milestone 6 payment will be on invoices presented with the appropriate documentation and will be paid after all cluster obligations have been met.

4.3 You acknowledge the Ministry’s expectation of transparency with regard to the use of funds paid to you under this agreement and agree to submit regular Disbursement Schedules showing how the payments made by the Ministry under this Agreement have been expended.

THIRD SCHEDULE – Payments… continued

5. Disbursements Schedule

This Schedule details how the amounts for Professional Fees, Professional Costs, and Operational Costs have been disbursed.

The schedule will include the following details:

| ###### ICT Professional Development Cluster |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract No. 09-0220 |  |  |  |  |  |  |  |  |  |
| Cluster Programme Disbursements Schedule |  |  |  |  |  |  |  |  |  |
| To: From: | Howard Baldwin Acting Manager, e-Learning unit Schooling Group Ministry of Education PO Box 1666 ### WELLINGTON 6011 Board of Trustees Sacred Heart Girl’s College, Hamilton |  |  |  |  |  |  |  |  |
| For Professional and Operational Costs: |  |  |  |  |  |  |  |  |  |
|  |  |  | 3yr Budget |  | Actual-to-date |  |  | Cumulative % |  |
| Professional Fees |  |  | $171164 |  | $ |  |  |  |  |
| Professional Costs |  |  | $66000 |  | $ |  |  |  |  |
| Operational Costs |  |  | $23336 |  | $ |  |  |  |  |
| Teacher Development Costs (if relevant) |  |  | $59500 |  | $ |  |  |  |  |
| plus Goods and Services tax |  |  | $4000 |  | $ |  |  |  |  |
| Total |  |  | $320000 |  | $ |  |  |  |  |